## Weekly project update
No | Cat. | Name | Description | Status | Start date | End date | Budget (RMB) | Budget Row ID | Budget Approval | GTS PM | Business PM or Keyuser | Sponser | Follow up action
1 | C | GZ WMS-CN 2026 Release 1 change | The enhancement of WMS-CN functions based on Business requirements | In Progress | 2026-01-01 | 2026-06-30 | 151500 | 25-5387 | Y | Rongtai Xiao | Xiaoming.Li Jinxia.Xu Boli.Peng | Emmy Wang Hao.Liu Josephine Chen | 1. 05.22 start QIOQ validation 2. 06.25 start PIQ validation 3 pending release system on 06.30
2 | C | GZ CCMS 2026 release 1 change | The enhancement of CCMS functions based on Business requirements | In Progress | 2026-03-19 | 2026-08-17 | 167192 | 25-5393 26-0512 | Y | Chao Lin | Simin.Liu Larry.Li | Xianqi.Yu | 1. 05.22 — Finish URS drafting. 2. 05.27 — Finish VP drafting. 4. 05.28 — Finish CCRB Approval 5. 06.25— Finish System Function Development
3 | I | Sox audit | WMS CN Sox audit support | Pending | 2026-06-01 | 2026-09-30 | NA | NA | NA | Rongtai Xiao | Tom Lin | Rick Weng | TBD
4 | I | EMA Response Follow Up | EMA audit content response and implementation of corrective measures | In Progress | 2026-04-01 | 2026-07-30 | NA | NA | NA | Rongtai Xiao | Zihua Chen | Helen Li | 1. EMA Response Follow Up: draft the response 2. WMS-CN Initiate a dedicated implementation plan to perform retrospective negative testing for specific roles access defined in the URS. 3. Global and local validation SOPs will be updated to include risk-based requirements for negative testing, ensuring that verification of unauthorized actions is systematically defined and implemented as part of validation activities.
5 | I | ECD (Acctrue) ADC line IOQ testing | ADC Line Acctrue IOQ testing supporting | In Progress | 2026-03-01 | 2026-08-30 | NA | NA | NA | Rongtai Xiao | Larry Li | Xianqi.Yu | 1. support the ADC Line Acctrue IOQ testing
6 | C | LIMS enhanced QC functionality ( MES , SAP Interface , 16+Enhancement) | To enhance QC functionality in LIMS (New MES interface and SAP interface optimization and 16 items) | In Progress | 2026-03-01 | 2026-09-15 | 952640 | 25-5345 | Y | Leo Sun | Boli.Peng Xuanbin Huang | Josephine Chen | 1 URS 2 CRs for Each Functions
7 | C | DP3 shop floor Wifi signal enhancement | Deploy additional ELAN and MLAN AP to achieve full Wi‑Fi coverage in the DP3 shop floor. | In Progress | 2026-04-24 | 2026-06-30 | 290000 | 26-0518 | Y | Jacky Zheng | Simin.Liu Haoken.Huang | Xianqi.Yu | 1.AP Cabling 2.Switch and AP configuration
8 | I | 2026 Annual GMP system data restoration test | Perform GMP data restoration tests on the "2026 Computerized system restore list" and complete the GZ‑13‑T‑027 test records. | In Progress | 2026-01-01 | 2026-12-31 | NA | NA | NA | Jacky Zheng | Qiuling Chen Jinfeng Xu Xiaochang Wu | Helen Li | Perform the DP/DS/QC GMP system data resotore test and complete"GZ-13-T-027" Test Record
9 | C | CR10074 Material master report ZMM066 enhancement package 2026 | 1.Add MPN material information 2. Extend manufacturer field length 3. Add material creation and change date/time, 4. Add "Plant-specific Mater” and “Do Not Cost” for finance 5.Support all data type display for characteristic, including CHAR,CURR,DATE,NUM,TIME 6.The display length of CHAR should align with the characteristic configuration | In Progress | Q1 2026 | Q2 2026 | AMS | NA | NA | Rolf Ding | Jason Xiang | Emmy Wang
10 | C | CR6610 WM configuration update package | 1. Add material type Z019 for PO inbound delivery UoM conversion enhancement 2. Update ATP check rule to include safety stock quantity 3. Set manufacturer as mandatory for MPN material creation | In Progress | Q2 2026 | Q2 2026 | AMS | NA | NA | Rolf Ding | Xiaoming Li | Emmy Wang
11 | C | CR10072 GTO BOM mass export report and GZ costing BOM role enablement | 1.Mass download production BOM 2.Update SAP role for costing BOM user access | In Progress | Q2 2026 | Q2 2026 | AMS | NA | NA | Rolf Ding | Winnie Liu; Jinxia Xu; Yanting Liang | Emmy Wang; Hao Liu; Xianqi Yu
12 | C | CR10070 GZ ZWM011 material inspection checklist form enhancement | 1. Fix material validation status error when having multiple PO at the same time during inbound delivery 2. Add ambient exposure reminder on the form by new material characteristics in classification 3. Update data logic to get the correct manufacturer address from validated vendor list enhancement | In Progress | Q2 2026 | Q2 2026 | AMS | NA | NA | Rolf Ding | Xiaoming Li | Emmy Wang
13 | C | CR10067 GTO recipe mass export report | Mass export product recipe as a global solution | In Progress | Q2 2026 | Q2 2026 | AMS | NA | NA | Rolf Ding | Winnie Liu; Jinxia Xu; Yanting Liang | Emmy Wang; Hao Liu; Xianqi Yu
14 | C | CR10069 GZ weighing center PDA material movement posting enhancement | SAP PDA scan weighing center barcode to perform stock movement type 311 & Z01 | In Progress | Q2 2026 | Q3 2026 | AMS | NA | NA | Rolf Ding | Xiaoming Li | Emmy Wang
15 | C | CR10096 GZ WMS stock label enhancement with SAP-WMS integration | 1.AS/RS warehouse and shopfloor WMS material master data interface separation by material type 2.Add user name printed WMS stock label triggered by WMS repack interface | In Progress | Q2 2026 | Q2 2026 | AMS | NA | NA | Rolf Ding | Xiaoming Li | Emmy Wang
16 | C | CR10066 GZ WM configurations and new storage condition | 1.Add 2 storage conditions 2.Add 2 pallet types 3.Add Tcode LS08 | In Progress | Q2 2026 | Q2 2026 | AMS | NA | NA | Rolf Ding | Xiaoming Li | Emmy Wang
17 | C | CR10043 GZ fix reservation form barcode print issue | Bugfix barcode display and scan issue on GZ reservation form and replace it with QR code | Completed | Q2 2026 | Q2 2026 | AMS | NA | NA | Rolf Ding | Xiaoming Li; Jinxia Xu; Yanting Liang | Emmy Wang; Hao Liu; Xianqi Yu
18 | I | GDMPA pentest fix | Penetration Testing Vulnerability Remediation for BeOne Guangzhou GDMPA Application | In Progress | 2026-04-01 | 2026-05-30 | 21226.42 | 26-0508 | Y | Zhijun Xie | Helen Li | Sean Wang | 3rd round rework and retest
19 | I | QC eyeC system investigation and expension to SC | Requirement confirmation with SC, plan the test for SC and to resolve current issue with QC | In Progress | 2026-04-01 | 2026-07-01 | NA | NA | NA | Zhijun Xie | Jason Xiang, Qiuping Zeng | Emmy Wang, Josephine Chen | 2026.07.30 complete the SC study test to fully test whether eyeC can meet SC requirements.
20 | P | EDW expansion for GZ MFG - Phase 1 | 1. SAP and MES data ingestion 2. EDW platform validation 3. MES data layer design implementation and validation (risk) 4. training | In Progress | 2026-03-12 | 2026-11-19 | NA | NA | NA | Zhijun Xie | Xiaolong Shi | Daisy Yao
21 | C | DHS-CN integration for PFS and ADC and BioTD | 1. All BioTD bioreactors BJ SH SZ GZ (risk, storage impact) 2. PFS shopfloor process equipment 3. ADC shopfloor process equipment | In Progress | 2026-04-01 | Q4 2026 | NA | NA | NA | Zhijun Xie | Jing Zhou Leo Xia Larry Li | Jara Lin Xianqi Yu
22 | I | DHS-CN Deviation handling | 1. storage solution evaluation(risk) | In Progress | 2026-05-08 | 2026-06-07 | NA | NA | NA | Zhijun Xie | Bin Huang Simin Liu Xingming Chen | Daisy Yao
23 | I | MES deviation | QE-032004_ Investigation Report 1.Abnormal timestamps in STR bioreactor temperature data retrieved from MES. | In Progress | 2026-05-14 | 2026-05-21 | NA | NA | NA | Eric Duan | Xiaohao Zang | Daisy Yao | The first draft has been completed. Start the approval process after the review is completed.
24 | I | MES incident | 1.HI-2026-037_The old temperature value was obtained from STR-D1-308. 2.HI-2026-041_The MES failed to obtain the measurement value of the 300kg floor scale WIT-D1-202. completed 3.HI-2026-047_The expiration date of the materials produced by DS is abnormal. completed 4.HI-2026-029_EBR generation error. completed 5.HI-2026-031_The tablet computer is running slowly. 6.HI-2026-034_PH value has returned to the previous value and the solution preparation display has expired. 7.HI-2026-041_The scale failed tare when the solution was being dispensed. | In Progress | NA | NA | NA | NA | NA | Eric Duan | Zifeng Xie Feng He Yanting Lan | Daisy Yao | Incident causal investigation.
25 | P | MES DS3 expansion | expansion MES to DS3 and enhancement for current function and process | In Progress | 2025.12.10 | 2027.03.29 | 2881500 | 26-0484 | Y | Jiarong Gao | Baiquan Wang | Daisy Yao | 1. development - on going 2. integration test - on going 3. SAT
26 | I | MES communication management | 1. real time MES key user list 2. create Email group | In Progress | NA | 2026.05.31 | NA | NA | NA | Eric Duan | NA | NA | collect current key user list
27 | I | Tech Month | 1. Guangzhou site panel with Yingqun Wang, Fan Yang and David Li. 2. 3 booths support and 2 booths lead. | In Progress | 2026.04.06 | 2026.05.28 | 10355.69 | 26-0760 | Y | Daniel Wu | Vivian Liao | David Li | Panel rehearsal , Booth setup
28 | C | GZ MFG IT EOL AP replace | The IT EOL AP of the GZ MFG need to replace, including the external antennas and the internal antennas. The APs are distributed in Building 2A, 3EC, DS2,FillFinish, PQ, WES, Warehouse, and DS3 | In Progress | 2026.01.01 | 2026.12.30 | NA | NA | Y | Ken Huang | Area user | NA | 1、wireless survey demo – Completed 2、wireless survey PO – Completed 3、site wireless survey – Intention 4、Confirm with the user whether there is a window replacement – Intention 5、device purchase – Intention 6、device arrival – Intention 7、AP Replace – Intention
29 | C | Replace the EOL Core switches of the DMZ | Replace the EOL Core switches of the DMZ | In Progress | 2026.11.01 | 2027.01.30 | NA | NA | Y | Ken Huang | Jack Zheng Rong Tai Jiarong Gao Zhijun Xie Sean Wu Leo Sun Rolf Ding Yuhan Zhu Xiaolong Shi Xunbing Huang | NA | 1、device purchase – Completed 2、PO – Completed 3、device arrival – Intention 4、CR – Intention 5、device configuration – Intention 6、Communication on production halt plan – Intention 7、device replace – Intention
30 | C | Replace the EOL distributed switches in the DMZ at the ADC | Replace the EOL distributed switches in the DMZ at the ADC | In Progress | 2026.01.01 | 2026.12.30 | NA | NA | Y | Ken Huang | Jack Zheng | NA | 1、device purchase – Completed 2、PO – Completed 3、device arrival – Intention 4、CR – Intention 5、device configuration – Intention 6、device replace – Intention
31 | C | Replace the OT EOL Bosch Firewall | Replace the OT EOL Bosch Firewall | In Progress | 2026.04.01 | 2026.12.30 | NA | NA | Y | Ken Huang | Bosch User | NA | 1、PoC CR and test – In Progress 2、device purchase – Completed 3、PO – Intention 4、device arrival – Intention 5、CR – Intention 6、device configuration – Intention 7、Communication with Bosch user on halt plan – Intention 8、device replace – Intention
32 | C | IT SD-WAN Upgrade and replace | GZ MFG IT 互联网香港出口设备升级替换 | In Progress | 2026.04.01 | 2026.08.31 | NA | NA | Y | Ken Huang | NA | NA | 1、device purchase – Completed 2、device arrival – Intention 3、device replace – Intention
33 | C | GZ MFG OT network device inspect | Inspect OT network devices | In Progress | 2026.06.01 | 2027.5.30 | NA | 26-0799 | Y | Ken Huang | NA | NA | 1、PO – Completed 2、Inspect – Intention
34 | I | DHS-MES supplementary verification for 16 bioreactors | CAPA-018767 | In Progress | 2026.05.21 | 2026.06.30 | NA | NA | NA | Eric Duan | Zhijun Xie | NA | 1. define validation scope 2. align validation strategy 3. create VPC and apply IOQ protocol document number 4. draft IOQ protocol 5. conduct IOQ 6. approve IOQ report
35 | I | MyEHS handover | 1. instance for GTO site 2. instance for commercial office | In Progress | TBD | TBD | NA | NA | NA | Jiarong Gao | Gavin Zhang | NA | 1. summarize file and information for GTO instance 2. summarize file and information for commercial office instance
36 | I | IT CR for MES tablet | MES Tablet Optimization (New Deployment, Decommissioning, and Transfer from WCS) MES终端平板优化（新增、退役及WCS转移） | In Progress | 2026.05.22 | 2026.06.30 | NA | NA | NA | Eric Duan | NA | NA | 1. IT CR register - Completed 2. IT CR draft 3. IT CR review 4. IT CR approval
37 | I | MES 50 tablets setup | Install OS and setup personalization , install all software. | In Progress | 2026.05.11 |  | NA | NA | NA | Daniel Wu | Jiarong Gao | NA | 1. 5 testing completed 2. Waiting for tablets deliver
38
39
40
41
42
43
44
45
46
Note on B1: Rongtai Xiao: P： Project C： Change I：Initiative

## Bi-weekly Team meeting
Follow-up activities
Date | Priority | Items | Responsible | Completed (Y/N) | Comments
2026-05-09 | High | Project progress information collection and visibility | Rongtai Xiao | N
| High | Project templates and tracking mechanism setup | Rongtai Xiao | N
| High | GZ site Project management tracking process and budget tracking process setup | Rongtai Xiao | N
2026-05-22 | Medium | 将项目计划重排后的最新进度与领导和SAP team同步 | Gavin Gao | N
| Medium | 确认数仓项目的数据层验证范围，并与数仓及纸仓团队分别沟通确认 | Zhijun Xie | N

## Config
Category | Status | Priority | Budget Approval
P | Intention | High | Y
C | In Progress | Medium | N
I | Completed | Low | NA
Pending
Cancelled